## Risk Register
Risks |  |  | Baseline Risk Level |  |  | Response
Risk ID | Cause | Effect | Likelihood | Severity | Overall Risk Level | Strategy | Mitigation
1 | Scope Creep | Uncontrolled changes and continious growth of scope. Innaccurate estimates and irrelevant product features that arent' in the requirements gets added. Can impact the project schedule and cost | 3 | 2 | 6 | Reduce | Document all requirements - Verify scope with team - identify what is necessary for the MVP - Change control processes will be set up.
2 | Communication | Misunderstanding of requirements - Inaccurate expectations - lack of information for impacted individuals | 2 | 5 | 10 | Accept | Important to contact Chester with any issues with the project - follow the guidelines set on discovering solutions. Speak to colleagues. Make sure attiude is assertive, to passive and too aggressive are poor combination for communication.
3 | Illness / Absence | Reduce available time to work and miss out on key development opportunities. This would contribute massively to any project delays and certainly affect the quality of the final product | 3 | 3 | 9 | Reduce | Eating well and communicating any issues had. Allow for a buffer in time schedule in case any unforeseen circumstances occur. The buffer will allow time to finish the project with quality and not be run down by constraints. Keep constant communication with the team and Chester.
4 | Loss of Data | Losing the project and the deliverables - would therefore be damaging to the brand and company | 2 | 5 | 10 | Avoid | Regular backups and strong version control using GitHub will limit the impact of any data loss.
5 | Version Control Management | Persistant errors could occur if version control is not managed. | 2 | 4 | 8 | Reduce |  | merging with the master branch should only be done when comfortable with individual branches. Regualar clones must be made. Back up data to external harddrives, OFF cloud based areas.
6 | GDPR focused risks | Loss of customer data - data security issues | 4 | 5 | 20 | Avoid | Handle data with care, ensuring data security protocol structure is followed. Encrypt data using official tools. Add security procedures when designing the datacase to ensure the information is secure.
7 | Desk Life | Lenghty periods spent sat at the desk can affect posture, mental health and cause other underlying conditions that can impact project quality. | 5 | 2 | 10 | Reduce | Regular breaks - workouts in the morning; focuse on core work to stay stablised and stretching to stay loose - keep the diet fairly clean - avoid the spiral - use proper equipment.

## Risk Matrix
Severity | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
Likelihood